## Sheet1
List of issues:
No. | Date added | SLD | Issue | Open/closed
1 |  | Options Menu | Menu bar on left: "Siulation" should be simulation | Closed
2 |  | All | All SLDs. Make heading of each SLD a larger font | Closed
3 |  | All | Power Available, as well as all values. Use only 2 decimal places for values. | Closed
4 |  | All | Is it possible to increase all font sizes | Closed
5 |  | All | Change "Desktop Studies Communication Tool" to "Distributed Restart - Desktop Exercise Simulation" | Closed
6 |  | Options Menu | Change "kv" to "kV" for all options | Closed
7 |  | Options Menu | Change "chapelcrossgretna1" to "Chapelcross - Gretna 1" | Closed
8 |  | Options Menu | Change "chapelcrossgretna2" to "Chapelcross - Gretna 2" | Closed
9 |  | Options Menu | Change "ewehillgretna" to "Ewe Hill 2 WF - Gretna" | Closed
10 |  | Options Menu | Change "Stevencroft33kV" to "Steven's Croft" | Closed
11 |  | Options Menu | Change "Minsca33kV" to "Minsca WF" | Closed
12 |  | Options Menu | Change "Ewehillwindfarm1" to "Ewe Hill 1 WF" | Closed
13 |  | Options Menu | Change "Ewehillwindfarm2" to "Ewe Hill 2 WF" | Closed
14 |  | Chapelcross33kV SLD | Solway references should be 378 instead of 678. | Closed
16 |  | EweHillWindFarm1 | Add Ewe Hill 1 WF Heading, add Ewe Hill 1 label to busbar | Closed
17 |  | EweHillWindFarm1 | Busbar and circuit breakers should be 781, not 761 (Minsca is 761) | Closed
18 |  | EweHillWindFarm1 | Need to add a "button" /slider where the user can select the MW output be produced in discrete. This is just a dummy control, but important for the simulation | Closed
19 |  | StevensCroft 33kV | Change "Generator Diesel" to "Emergency Generator" | Closed
20 |  | StevensCroft 33kV | Need to add a "button" to "start" Stevenscroft generator. Select this button should turn the generator green | Closed
21 |  | N/A |  | closed
22 |  | Minsca33kV | Need to add a "button" /slider where the user can select the MW output be produced in discrete. This is just a dummy control, but important for the simulation | closed
23 |  | EweHillWindFarm2 | Add Ewe Hill 2 WF Heading, add Ewe Hill 2 label to busbar | Closed
24 |  | EweHillWindFarm2 | Need to add a "button" /slider where the user can select the MW output be produced in discrete. This is just a dummy control, but important for the simulation | Closed
25 |  | StevensCroft 33kV | Add Stevenscroft label above busbar | Closed
26 |  | StevensCroft 33kV | Move 699 labels a little closer to breakers | Closed
27 |  | StevensCroft 33kV | Add loadbank as per separate diagram | Closed
28 |  | StevensCroft 33kV | Auxiliary transformer doesn't change colour in step 1 | Closed
29 |  | Chapelcross33kV SLD | Add loadbank as per separate diagram | Closed
30 |  | Chapelcross33kV SLD | Add MW, MVAr measurements to Grid T1 transformer | Closed
31 |  | Chapelcross33kV SLD | Add transformer loads below each of (brown) arrows at the primary substations | Closed
32 | 2021-05-15 | Minsca33kV | Move 761 labels a little closer to breakers | Open | Minor
33 |  | Minsca33kV | Generator and WTG transformers need to change colour in step 4. They can be grouped. Not sure what the tagname is. | Closed
34 | 2021-05-15 | Minsca33kV | MW and MVAR measurements need to be added to SLD | Open | Calc
35 |  | Minsca33kV | Auxiliary transformer on far right should be coloured together with rest of wind farm. | Closed
36 |  | EweHill WindFarm 1 | Move 781 labels a little closer to breakers | Closed
37 |  | EweHill WindFarm 1 | Generator and WTG transformers need to change colour in step 6. They can be grouped. Not sure what the tagname is. | Closed
38 | 2021-05-15 | EweHill WindFarm 1 | MW and MVAR measurements need to be added to SLD | Open | Calc
39 |  | EweHill WindFarm 2 | Move WG2 label close to breaker. Can we change the label text to "CUSTOMER" to match the other wind farms? | Closed
40 |  | EweHill WindFarm 2 | Generator and WTG transformers need to change colour in step 15. They can be grouped. Not sure what the tagname is. | Closed
41 | 2021-05-15 | EweHill WindFarm 2 | MW and MVAR measurements need to be added to SLD | Open | Calc
42 |  | EweHill WindFarm 2 | GT1 transformer needs to change colour in step 12. Not sure what the tagname is. Same applies to the auxiliary transformer on the left | Closed
43 | 2021-05-15 | EweHill WindFarm 2 | Power Available should be 38MW, not 0. | Open | Minor
44 |  | Chapelcross132kV SLD | Box with Steven Croft measurements - only use 2 or 3 decimals | Closed
45 |  | Chapelcross132kV SLD | The Solway Bank windfarm block we should perhaps replace with the Ewe Hill 1 Windfarm measurement data, considering that we're not using Solway Bank | Closed
46 | 2021-05-15 | All diagrams | We need to include the busbar voltages and frequency (Hz) as per the CSV files | Open | Minor
47 | 2021-05-19 | StevensCroft 33kV | Need to add "LOAD BANK" text below symbol | Open | Minor
48 | 2021-05-19 | StevensCroft 33kV | Move "EMERGENCY GENERATOR" little lower so it doesn't overlap with symbol | Open | Minor
49 | 2021-05-19 | StevensCroft 33kV | Stevenscroft should be "Steven's Croft" - labels on busbar and heading. | Open | Minor
50 | 2021-05-19 | StevensCroft 33kV | pu measurement should next to top busbar. Amps should be below MW and MVAR next to generator | Open | Minor
51 | 2021-05-19 | StevensCroft 33kV | Need to add MW measurement linked to Load bank | Open | Calc
52 | 2021-05-19 | Chapelcross 33kV | Stevenscroft should be "Steven's Croft" | Open | Minor
53 | 2021-05-19 | Minsca33kV | % measurement? | Open | Minor
54 | 2021-05-19 | Minsca33kV | Bottom part of aux trfr needs to change to pink in step 4 | Open | Minor
55 | 2021-05-19 | Minsca33kV | pu measurement should next to top busbar | Open | Minor
56 | 2021-05-19 | Ewe Hill WF 1 | Auxiliary trfr needs to change colour (both parts) on step 6 together with busbar | Open | Minor
57 | 2021-05-19 | Ewe Hill WF 1 | pu measurement should be next to top busbar | Open | Minor
58 | 2021-05-19 | Ewe Hill WF 1 | "Power available" in box should be 12MW | Open | Minor
59 | 2021-05-19 | Ewe Hill WF 2 | % measurement? | Open | Minor
60 | 2021-05-19 | Ewe Hill WF 2 | Aux trfr on the left - small circle should be pink when the rest is energised. Little part of earthing trfr (small line) on the left shows green from step 12 onwards, should be pink as well, or remove. | Open
61 | 2021-05-19 | Ewe Hill WF 2 | Auxiliary trfr needs to change colour (both parts) on step 14 together with busbar | Open
62 | 2021-05-19 | Ewe Hill WF 2 | Line sticking out on the left of WTG14 should be removed | Open
63 | 2021-05-19 | Ewe Hill WF 2 | V (pu) measurements to be added next to busbar | Open
64 | 2021-05-19 | Chapelcross 132kV | Not sure what % measurement is? | Open
65 | 2021-05-19 | Chapelcross 132kV | Move 33kV BB a little lower so that there is a bit of a gap between the line and the Minsca WF box, or move the boxes on the left up - whichever is easiest. | Open
66 | 2021-05-19 | Chapelcross 132kV | Aux trfr on the left at T1 - small circle should be pink | Open
67 | 2021-05-19 | Gretna 400kV | Not sure what % measurement is? | Open
68 | 2021-05-19 | Gretna 400kV | Aux trfr on the left - small circle should be pink when the rest is energised in step 11 | Open
69 | 2021-05-19 | Gretna 400kV | Need to add pu measurement next to both busbars | Open
70 | 2021-05-19 | Gretna 400kV | Need to add MW, MVAR measurement to SGT1 circuit | Open
71 | 2021-05-19 | Gretna 132kV | Not sure what % measurement is? | Open
72 | 2021-05-19 | Gretna 132kV | Need to add pu measurement next to busbar | Open
73 | 2021-05-19 | Gretna 132kV | Need to add MW, MVAR measurement to all circuits | Open
74 | 2021-05-19 | Chapelcross-Gretna 1 | Need to add pu measurement next to busbars (both ends) | Open
75 | 2021-05-19 | Chapelcross-Gretna 1 | Not sure what % measurement is? | Open
76 | 2021-05-19 | Chapelcross-Gretna 2 | Need to add pu measurement next to busbars (both ends) | Open
77 | 2021-05-19 | Chapelcross-Gretna 2 | Need to add MW, MVAR and Amps measurements (even though they will be zero) | Open
78 | 2021-05-19 | Ewe Hill - Gretna | Not sure what % measurement is? | Open
79 | 2021-05-19 | Ewe Hill - Gretna | Place pu measurement next to busbar at top | Open
80 | 2021-05-19 | Ewe Hill - Gretna | Aux trfr on left - left circle should be pink from step 12 onwards | Open
81 | 2021-05-19 | Ewe Hill - Gretna | Need to add MW, MVAr, amps, and V measurements next to ILA3 | Open
82 | 2021-05-19 | Ewe Hill - Gretna | Need to add MW, MVAR, amps and V measurements to the left of 805 | Open
83 | 2021-05-19 | Chapelcross 33kV | Remove power available box from Solway bank | Open
84 | 2021-05-19 | Chapelcross 33kV | Add EweHill 2 WF to bar chart | Open
85 | 2021-05-19 | Chapelcross 33kV | Possibly move bar chart a little lower - the heading of the table looks like it belongs to Newcastleton | Open
86 | 2021-05-19 | Chapelcross 33kV | MVA measurements from primary substations disappear in the step that they update and reappear again. Values no longer are %. Looks like values may need to be divided by 100 at present. We can discuss, as this something we can change in the lookup table if you want to keeps simpler. | Open
87 | 2021-05-19 | Chapelcross 33kV | We will provide a new table shortly that outputs MW values and we'll display these instead of the MVA measurements, so just a headsup all the "MVA"s at the primary substations will need to change to "MW" | Open
88 | 2021-05-19 | Chapelcross 33kV | Need to add amps values next to 698-22, 698-23, 698-24 | Open
89 | 2021-05-19 | Chapelcross 33kV | Need to add load bank measurement to load bank - MW value | Open
90 | 2021-05-19 | Chapelcross 33kV | Grid 1 trfr - left ring of aux transformer should be pink when energised | Open
91 | 2021-05-19 | Chapelcross 33kV | Need to add MW, Mvar, and amps next to Grid 1 trfr | Open
92 | 2021-05-19 | Chapelcross 33kV | Move pu measurement next to busbar on left | Open
93 | 2021-05-19 | Chapelcross 33kV | All diagrams - add arrows to indicate current flow - this to be done last | Open
94 | 2021-05-19 | Back-end | When in DER role, need to add a button to move to next SLD after the DER has been energised, to allow MW and MVAr values to be confirmed with the DNO | Open
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133